## DTT Test Hour Log
Instruction: Fill in the number of hours that were required to complete the test. Please include every step you took during the process and include a detailed description of every step. Add reasoning on why you took certain decisions or applied specific techniques. We prefer quality over quantity so take your time with the test and the log.
Subject | Amount of hours | Date | Description | Bonus
Research maze algorithm | 30m | 2023-12-13 | Read trough wikipedia and chose a suitable algorithm
Create project and git repository | 5m | 2023-12-13 | Made a simple uity project and put in on github
Generation algorithm | 3h | 2023-12-18 | Took me longer than expected because I made a mistake that I didn't find immediatly
In editor UI | 19m | 2023-12-18 | Added a button to generate a maze in editor time
In game UI | 2h | 2023-12-20 | Used Kenney assets to set up a simple scalable UI
Step by step generation | 44m | 2023-12-21 | Modified the generation so that it records what it does in a 'history' and then I delete uneeded wall step by step according to that | X
Fix camera positioning | 46m | 2023-12-21 | Made the camera scale so that the entire maze fits in it. It was a bit trixky because I can only set the height and the width is determined by the acpect ratio so I decided to sometimes rotate the camera
Camera movement | 56m | 2023-12-22 | Added a separete mode for the camera where you can more it around with the mouse
Fix ClearMaze() function | 29m | 2024-01-03 | I encountered a weird bug that makes it so that it's difficult do delete objects at editor time.
3D representation | 31m | 2023-12-13 | Used some Kenney asssets to make a dungeon like maze | X
Polish and clean up | 2h 47m | 2024-01-03 | Added comments and rewrote some things in a cleaner way
Total amount of hours | 12h 7m